Project Charter

Customer Portal Revamp

| Sponsor | Project Manager | Start Date | Target End Date |
| --- | --- | --- | --- |
| Ayesha Khan (VP Engineering) | Umar | 2026-08-01 | 2026-11-15 |

# 1. Purpose & Business Case

The current customer portal has a checkout abandonment rate of 34% and generates frequent support tickets about navigation. This project rebuilds the portal on the new design system to reduce friction and support load.

# 2. Objectives

- Reduce checkout abandonment rate from 34% to under 20%

- Cut portal-related support tickets by 40%

- Migrate portal to the new design system for consistency with other products

# 3. Scope

In scope

- Redesign of checkout flow

- Redesign of account settings pages

- Migration to new design system components

Out of scope

- Backend payment processor changes

- Mobile app updates (separate project)

- New feature development beyond the redesign

# 4. Stakeholders & Roles

| Name | Role | Responsibility |
| --- | --- | --- |
| Ayesha Khan | Sponsor | Budget approval, escalation path |
| Umar | Project Manager | Delivery, coordination, reporting |
| Bilal Ahmed | Tech Lead | Architecture decisions, code review |

# 5. Timeline & Milestones

| Milestone | Target Date |
| --- | --- |
| Design sign-off | 2026-08-20 |
| Checkout flow complete | 2026-09-30 |
| Account settings complete | 2026-10-20 |
| Launch | 2026-11-15 |

# 6. Budget & Resources

Estimated $85,000 covering 2 FTE-months of design and 4 FTE-months of engineering.

- 1 Product Designer (0.5 FTE)

- 2 Frontend Engineers (1 FTE each)

- 1 QA Engineer (0.5 FTE)

# 7. Risks & Assumptions

Known risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Design system components not ready in time | High | Weekly sync with design systems team; fallback to custom components if blocked |
| Scope creep from stakeholder requests | Medium | Change requests routed through sponsor approval |

Assumptions

- Design system team can support integration questions within 1 business day

- No major backend API changes required during this period

# 8. Success Criteria

- Checkout abandonment under 20% within 30 days of launch

- Support tickets related to portal navigation down 40% within 60 days

- Zero critical bugs in production at 2 weeks post-launch

# 9. Approval

By signing below, the sponsor and project manager confirm authorization to proceed.

| Sponsor Signature | Date |
| --- | --- |

| Project Manager Signature | Date |
| --- | --- |